## Gantt Chart
Project Name: | ABC Test
Project Start: | 2024-01-10
Today's Date: | 2024-02-26
Weeks in Progress: | 7
[6 empty] | 2024-01-10 | 2024-01-17 | 2024-01-24 | 2024-01-31 | 2024-02-07 | 2024-02-14 | 2024-02-21 | 2024-02-28 | 2024-03-06 | 2024-03-13 | 2024-03-20 | 2024-03-27 | 2024-04-03 | 2024-04-10 | 2024-04-17 | 2024-04-24 | 2024-05-01 | 2024-05-08 | 2024-05-15 | 2024-05-22 | 2024-05-29 | 2024-06-05 | 2024-06-12 | 2024-06-19 | 2024-06-26
Task | Project Lead | Start Date | End Date | Days | Progress | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Planning Stage
Task 1 | Mike Smith | 2024-01-10 | 2024-02-29 | 50 | 80%
Task 2 | Sarah Lee | 2024-01-19 | 2024-03-29 | 70 | 100%
Task 3 | Arnold West | 2024-02-07 | 2024-03-26 | 48 | 70%
Task 4 | Jeff Shunar | 2024-02-22 | 2024-04-28 | 66 | 100%
Execution Stage
Task 1 | Travis Scor | 2024-03-02 | 2024-04-03 | 32 | 30%
Task 2 | Verna Hum | 2024-03-22 | 2024-05-21 | 60 | 50%
Task 3 | Raleigh Lee | 2024-03-30 | 2024-05-09 | 40 | 50%
Task 4 | Jess Yuan | 2024-04-06 | 2024-05-31 | 55 | 100%
Task 5 | Anna Glen | 2024-04-13 | 2024-05-13 | 30 | 80%
Review Stage
Task 1 | Mike Smith | 2024-03-24 | 2024-04-25 | 32 | 30%
Task 2 | Sarah Lee | 2024-04-01 | 2024-05-31 | 60 | 50%
Task 3 | Arnold West | 2024-04-09 | 2024-05-19 | 40 | 50%
Note on A3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Enter project Start date and Today’s date beneath for accurate project tracking

## kelvin cookie
Bake biggest chocolate chip cookie in the world
Tasks | Start Date | Days Needed | Completion | Adjusted Length
Secure location | 2023-08-01 | 15 | 2023-08-22 | 21
Order ingredients | 2023-08-01 | 30 | 2023-09-12 | 42
Notify Guinness World Records | 2023-08-15 | 5 | 2023-08-22 | 7
Invite press & participants | 2023-09-10 | 10 | 2023-09-22 | 12
Build solar reflecting oven | 2023-09-05 | 8 | 2023-09-15 | 10
Final prep | 2023-09-20 | 7 | 2023-09-29 | 9
Event day | 2023-10-01 | 1 | 2023-10-02 | 1

## test
Task | Start Date | Days to Complete
Task 1 | 2024-05-22 | 13
Task 2 | 2024-05-31 | 9
Task 3 | 2024-06-05 | 9
Task 4 | 2024-06-15 | 14
Task 5 | 2024-06-21 | 9
Task 6 | 2024-06-01 | 5
Task 7 | 2024-07-08 | 7
Task 8 | 2024-07-15 | 12